## Sheet1
Sprint Retrospective for Driver alerts system Project
| What went well | What didn’t go well | Action Item(s)
Sprint 1 | 1. Able to set up the AWS Data source successfully 2. Develop the Register and login page. 3. Spike for gathering the information for Face Detection using python. | Not able to store the Registered information in the database | Need to setup data services to store the information in data base
Sprint 2 | 1. Able to setup data services for Registration and login page 2. Finalized the implementation of face detection using python | Initially we were facing challenges with python version for the implementation of face detection | We had to degrade our python version for the implementation of face detection
Sprint 3 | 1. Able to develop face detection functionality. 2. Able to test the code and fix the issues within the sprint. 3. Forgot password. | Requirements have been changed | Traffic Sign Recognition (TSR) on priority
Sprint 4 | 1. Spike for gathering the information for Traffic Sign Recognition 2. Started Initial draft documentation for Face detection 3. Testing different scenarios for face detection functionality. | Face Detection documentation was not in detail. | Will work on changes in the documentation (Face Detection) as per the suggestions Will start the Documentation for Traffic sign Recognition
Sprint 5 | 1. Started Initial draft documentation for Traffic sign recognition. 2. Face detection documentation changes are in progress | None | Will continue to work on improving documents so that we can make it more detail.